|  |  |
| --- | --- |
| **Project information** | |
|  |  |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1256 |
| PRIORITY AXIS: | 2.Environment and Emergency Preparedness |
| MEASURE: | 2.1 Improve systems and approaches to address cross-border environmental challenges, protection and management |
| PROJECT TITLE: | **Flood prevention - for better life quality** |
| ACRONYM: | Flood EM |
| DURATION[[1]](#footnote-1): | 23.01.2014 – 22.04.2016 |
| IPA FUNDS CONTRACTED: | 819.671,15 € |
| TOTAL FUNDS CONTRACTED: | 964.319,00 € |
| ABSORBTION RATE (%)[[2]](#footnote-2): | 90,87 % |

|  |  |
| --- | --- |
| PROJECT OBJECTIVE(S): | * Improving the quality of life in the cross boarder and Danube area by raising the level of the emergency situations management and preparedness in Resita and Kikinda. * Increasing technical and human capacities of people involved in the emergency situations field. * Developing joint planning in emergency situations and dialogue between decision makers. * Creating cross-border connections among people involved in the emergency situations field. |
| SHORT DESCRIPTION OF THE PROJECT: | Through implementation of this project the partners purchased emergency intervention equipment; they developed an Emergency Situations Common Strategy, creating cross border connections among people involved in the emergency situations field. |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DEGREE OF ACHIEVEMENT OF INDICATORS[[3]](#footnote-3): | |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | Indicator | Indicator value provisioned in the contract | | Present indicator value | | % 6= (5)/(3)\*100 | | Output indicators  (1) | UM  (2) | Quantity  (3) | UM  (4) | Quantity  (5) |  | | Increased qualification of human resources in reacting to emergency situations | Number of experience exchanges and common drills | 4 | Number of experience exchanges and common drills | 4 | 100% | | Increasing joint planning in emergency situations | Number of common strategies regarding emergency situations | 1 | Number of common strategies regarding emergency situations | 1 | 100% | | Increased capacity of municipalities in emergency situations reacting | Equipment obtained | 12 | Equipment obtained | 12 | 100% | | **Result indicators** |  |  |  |  |  | | Increased institutional capacity and preparedness in reacting to situations of environmental emergency (e.g. flooding, bird flu, swine influenza) | action plans or regional cross border strategies | 1 | action plans or regional cross border strategies | 1 | 100% | |

|  |  |
| --- | --- |
| RESULTS ACHIEVED, INCLUDING PHOTOS: | - 1 Emergency Situation Common Strategy elaborated;  - 2 common drill organized;  - Emergency intervention equipment procured (1 emergency auto vehicles with high debit moto-pump, 1 emergency auto vehicles with telescopic basket, 1 emergency auto vehicles with water tank, 1 excavator, 5 large capacity tents and 5 inflatable boats);  - 1 Hydraulic excavator and its additional equipment;  -1 Hydraulic excavator attaching drill;  -1 Hydraulic excavator transporting trailer;  -1 Hydraulic excavator grabs for digging attachment;  -1 Hydraulic excavator cropper attachment;  - Revitalized 50 km of canal network in cross border area in municipality of Kikinda area. |
| Short video about the project | <https://www.youtube.com/watch?v=QyreoKbLt8o> |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Partnership information** |  | | | | |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | MUNICIPALITY OF RESITA | Romania | Caras-Severin | 635.118,00 | Resita, Piata 1 Decembrie 1918, no. 1 A  Tel. 0255/215314 |
| PARTNER 2: | Municipality of Kikinda | Serbia | North Banat | 329.201,00 | Kikinda, Trg srpskih dobrovoljaca 12 |



1. the implementation period (including extensions) [↑](#footnote-ref-1)
2. total funds spent/total funds contracted \*100 [↑](#footnote-ref-2)
3. indicators and level of achievement against targets set [↑](#footnote-ref-3)