
|  |  |
| --- | --- |
| **Project information** | |
|  |  |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1329 |
| PRIORITY AXIS: | 1.Economic and Social Development |
| MEASURE: | 1.2 Develop the tourism sector, including the strengthening of the regional identity of the border region as a tourist destination |
| PROJECT TITLE: | **Promoting tourist attractions in border areas Drobeta** |
| ACRONYM: | PTABAD |
| DURATION[[1]](#footnote-1): | 12.06.2013 – 11.06.2014 |
| IPA FUNDS CONTRACTED: | 260.287,00 |
| TOTAL FUNDS CONTRACTED: | 306.220,00 |
| ABSORBTION RATE (%)[[2]](#footnote-2): | 85,09 |
| PROJECT OBJECTIVE(S): | To achieve on the basis of joint cross-border projects and common actions by Romanian and Serbian stakeholders a more balanced and sustainable socio-economic development of the Romania-Serbian border area.  To promote a brand and a genuine sustainable tourism product specific to the border area. |
| SHORT DESCRIPTION OF THE PROJECT: | Inventory of the main forms of tourism practiced in the border cities of Drobeta Turnu Severin (Romania) and Negotin (Serbia) was achieved through this project. Seminars and tourist workshops were organized in order to promote tourism, DVD documentary film highlighting the attractiveness of tourism and in order to promote natural, historical and cultural border area was created. 750 Travel catalogues, 750 Travel guides, 600 Colour photos, 600 Flyers, 110 Polyurethane panels, 9 advertising TV Spots, 8 advertising RADIO Spots and 500 DVDs were printed for the promotion of the tourist offer of Drobeta and Negotin. Three tourism fairs were organized in Negotin, Drobeta Turnu Severin and in Timisoara. |
| DEGREE OF ACHIEVEMENT OF INDICATORS[[3]](#footnote-3): | |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **Indicator**  **(1)** | **Indicator value provisioned in the contract** | | **Present indicator value** | | **%**  **6= (5)/(3)\*100** | | **Output indicators**  **(1)** | **UM**  **(2)** | **Quantity**  **(3)** | **UM**  **(4)** | **Quantity**  **(5)** |  | | **Project indicators** |  |  |  |  |  | | PROMO TV-1 | PCS | 9 | PCS | 9 | 100% | | RADIO SPOT | PCS | 8 | PCS | 8 | 100% | | WORKSHOPS | PCS | 3 | PCS | 3 | 100% | | On line banner advertising | PCS | 5 | PCS | 5 | 100% | | Tourism fair | PCS | 3 | PCS | 3 | 100% | | Promotional materials:  Travel catalog  Travel guide  Poster  Color photos  Flyers  Photo albums | PCS | 750  1250  156  600  600  500 | PCS | 750  1250  156  600  600  500 | 100%  100%  100%  100%  100%  100% | | DVD | PCS | 500 | PCS | 500 | 100% | | Data base | PCS | 1 | PCS | 1 | 100% | | **Result indicators** |  |  |  |  |  | | New or improved cross-border tourism products and services | Number of activities, actions, initiatives focusing on promoting tourism in the border area | Aprox.4000 promotional materials | Number of activities, actions, initiatives focusing on promoting tourism in the border area | 4357 | 100% | |
| RESULTS ACHIEVED: | Identification of touristic products of interest in the border area.  Creation of a database to act as network hub to choose the destination countries.  Creation and dissemination of promotional materials.  Three seminars and three thematic workshops organized in order to promote the urban tourism area in relation to the border area Drobeta Turnu Severin – Negotin.  Creation of a local tourism brand.  Organization of promotion fairs in Negotin, Drobeta Turnu Severin and Timisoara. |
|  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Partnership information** |  | | | | |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | Drobeta Turnu Severin City Hall | Romania | Mehedinti | 161.434,00 | Drobeta Turnu Severin, 2 Maresal Averescu Street  Tel. 40252314379 |
| PARTNER 2: | Negotin Municipality | Serbia | Bor | 60.782,00 | Negotin, Trg Stevana Mokranjca  Tel. + 381 19 544 000 |
| PARTNER 3: | Mehedinti Tourism Association | Romania | Mehedinti | 84.004,00 | Drobeta Turnu Severin, 25 Crisan street  Tel. 4 0745238478 |





1. the implementation period (including extensions) [↑](#footnote-ref-1)
2. total funds spent/total funds contracted \*100 [↑](#footnote-ref-2)
3. indicators and level of achievement against targets set [↑](#footnote-ref-3)