| Project information |  |
| --- | --- |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1345 |
| PRIORITY AXIS: | 1.Economic and Social Development |
| MEASURE: | 1.1 Support for local/regional economic and social infrastructure |
| PROJECT TITLE: | Point for Crossing the Danube by Ferry between Moldova Noua and Golubac Localities |
| ACRONYM: | Moldova Noua Ferry |
| DURATION: | 13.12.2013 – 31.12.2016 |
| IPA FUNDS CONTRACTED: | 1.999.772,39 |
| TOTAL FUNDS CONTRACTED: | 2.352.673,40 |
| ABSORBTION RATE (%): | 42,07 |
| PROJECT OBJECTIVE(S): | Balanced economic and social development of the Danube Clisura - border area between Serbia and Romania, through promoting of joint actions to stimulate cross-border economic relations, while supporting economic diversification and capitalizing the historical, cultural and natural values in the framework of joint cross-border projects aiming development of inter-modal transport infrastructure and economic services. Increasing the overall competitiveness of the economy in Moldova Noua and Golubac areas by making inter-modal river transport infrastructure. Stimulation of interregional cross-border cooperation by promoting economic exchanges on both Danube shores, as the main means of economic and social development. Increasing life quality of communities from Danube Clisura cross-border area, by achieving an integrated economic and touristic offer and a program of Romanian-Serbian joint actions. |
| SHORT DESCRIPTION OF THE PROJECT: |  |
| DEGREE OF ACHIEVEMENT OF INDICATORS: | Immediate Result indicators (output); The value of the indicator set forth by the contract; The value of the indicator reported in the previous reports; The value of the indicator reported during the current period of reporting; The total achievements up to date; Differences compared to the values set forth in the contract. Name; UM; Quantity; Quantity; Quantity; Quantity; (±%). New or improved cross-border transport links and new or improved logistics capacity in the border area; The number of activities, actions, initiatives to create new transport links or improve existing transport links or addressing logistical capacity; - 1 Point for crossing the Danube by ferry-boat for passengers and auto vehicles in Moldova Noua; - 1 Point for crossing the Danube by ferry-boat for passengers and auto vehicles in Usije, Golubac Municipality; - 1 Romanian border crossing point in Moldova Noua; - 1 Connection road to DN57 in Moldova Noua; - 1 Link road in Usije; Connection road Usije- Veliko Gradiste.; 0; 0; 0; 100%. Result indicators; The value of the indicator set forth by the contract; The value of the indicator reported in the previous reports; The value of the indicator reported during the current period of reporting; The total achievements up to date; Differences compared to the values set forth in the contract. Name; UM; Quantity; Quantity; Quantity; Quantity; (±%). Making an inter-modal river transport infrastructure and a border crossing point with direct implications on investment attractiveness, economic and social development and tourism of the Moldova Noua, Golubac and Veliko Gradiste; Surface of the general platform made in the project (sqm); 2472 sqm; 0; 0; 0; 0%. Surface of the sidewalks made ​​in the project (sqm); 272; 0; 0; 0; 0%. Length of the ramp (m); 20; 0; 0; 0; 0%. Length of Danube bank protection (m); 2x60; 0; 60; 60; 50%. Length of fencing (m); 300; 0; 0; 0; 0%. Length of the rehabilitated connection road to DN57 (m); 1200; 0; 0; 0; 0%. Length of the rehabilitated connection road ferry access Usije (m); 450; 0; 198; 0; 44%. Length of the rehabilitated connection road to Veliko Gradiste (m); 7449; 0; 0; 0; 0%. number of ferries purchased; 1; 0; 0; 0; 0%. Number of pontoons purchased; 1; 0; 0; 0; 0%. Number of the new border crossing points opened; 1; 0; 0; 0; 0%. Number of border crossings through the new point/ year; 10000; 0; 0; 0; 0%. Increasing the economic and tourism interest for Moldova Noua, Golubac and Veliko Gradiste localities and their surroundings; Number of new economic agents appeared in Moldova Noua, Golubac and Veliko Gradiste area; 8; 0; 0; 0; 0%. - Dynamics of local revenues obtained from taxes and contributions on economic activities; X+n; 0; 0; 0; 0%. The turnover of the touristic services in the area; X+n; 0; 0; 0; 0%. Annual number of tourists (number of nights spent in Moldova Noua, Golubac and Veliko Gradiste localities); - 13000; 0; 0; 0; 0%. Annual growth in the number of tourists; 5%; 0; 0; 0; 0%. Increasing life quality of inhabitants in Moldova Noua, Golubac and Veliko Gradiste localities; Increasing annual income per capita in the city of Moldova Noua; - Y+M; 0; 0; 0; 1 0%. Increasing annual income per capita in the Golubac municipality; - Y+M; 0; 0; 0; 0%. Increasing annual income per capita in the Veliko Gradiste municipality; - Y+M; 0; 0; 0; 0%. Creation of new permanent jobs; - Number of newly created permanent jobs; - 20; 0; 0; 0; 0%. - Number of persons employed in the system compared to the one proposed by the project; - 20+n; 0; 0; 0; 0%. |
| RESULTS ACHIEVED: | R1: Realization of an inter-modal river transport infrastructure and of a border crossing point with direct implications on the investment attractiveness, economic and social development and tourism in the Moldova Noua-Golubac border area: 1 ferry was purchased, connection road to ferry access Usije rehabilitated and new border crossing point on the Serbian side was constructed (but it is not functional yet). R2: Increasing the economic and tourism interest for Moldova Noua and Golubac localities and their surroundings - Not the case yet R3: Increasing life quality of inhabitants in Moldova Noua and Golubac - Not the case yet R4: Creation of new permanent jobs - Not the case yet |

| Partnership information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | Caras-Severin County Council | Romania | Caras-Severin | 1.008.383,80 | Resita, Piata 1 Decembrie No.1 Tel. 40 255 211 420 |
| PARTNER 2: | City of Moldova Noua | Romania | Caras-Severin | 656.449,60 | Moldova Noua, Nicolae Balcescu street, no.26 Tel. 0 255 540997 |
| PARTNER 3: | Golubac Municipality | Serbia | Branicevski | 247.071,00 | Golubac, Cara Lazara 15 Tel. +38112678128 |
| PARTNER 4: | Veliko Gradiste Municipality | Serbia | Branicevski | 440.769,00 | Veliko Gradiste, Zitni Trg 1 Tel. +381 12 662 120 |

the implementation period (including extensions)

total funds spent/total funds contracted *100

indicators and level of achievement against targets set