|  |  |
| --- | --- |
| **Project information** | |
|  |  |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1387 |
| PRIORITY AXIS: | 3. Promoting “people to people” exchanges |
| MEASURE: | 3.1 Support the development of civil society and local communities |
| PROJECT TITLE: | **Social Equal Opportunities** |
| ACRONYM: | SEO |
| DURATION[[1]](#footnote-1): | 05.04.2013 – 04.06.2014 |
| IPA FUNDS CONTRACTED: | 220.915,00€ |
| TOTAL FUNDS CONTRACTED: | 259.900,00€ |
| ABSORBTION RATE (%)[[2]](#footnote-2): | 94,62% |

|  |  |
| --- | --- |
| PROJECT OBJECTIVE(S): | Creating conditions for the inclusion of Roma population.  Increasing the level of awareness among Roma population regarding health, education and employment.  Establishing of new working places for most vulnerable social group – Roma women. |
| SHORT DESCRIPTION OF THE PROJECT: | Hemofarm Foundation and Gipsy Woman Association for Our Children have jointly prepared the project in order to support the Roma population in the region by training 15 Roma women in the field of education, health and employment, visiting 500 Roma families in order to gain the opportunity to get employed, educating 30 children by raising their interest to go to school, organizing a sport tournament and a music festival. |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DEGREE OF ACHIEVEMENT OF INDICATORS[[3]](#footnote-3): | | **Indicator** | **Indicator value provisioned in the contract** | | **Present indicator value** | | **% 6= (5)/(3)\*100** | | --- | --- | --- | --- | --- | --- | | **Output indicators**  **(1)** | **UM**  **(2)** | **Quantity**  **(3)** | **UM**  **(4)** | **Quantity**  **(5)** |  | | **Project indicators** | | | | | | | Roma women educated regarding employment, health and education | Number of educated Roma women | 10 | Number of educated Roma women | 10 | 100 | | Roma children trained on the topic of education | Number of children trained | 30 | Number of children trained | 30 | 100 | | Roma women trained by Roma women | Number of trained women | 50 | Number of trained women | 50 | 100 | | Sport tournament organized | Number of organized tournaments | 1 | Number of organized tournaments | 1 | 100 | | Music Festival implemented | Number of implemented festivals | 1 | Number of implemented festivals | 1 | 100 | | Study tour implemented | Number of participants | 1 | Number of participants | 1 | 100 | | Project promoted to a professional and wider public | Number of different types of promo material | 4000-flyers  2000· educational material  2-billboard,  2000·brochure  4000f·layers,  2000· educational materials 1,  2000· educational materials 2,  5000· educational materials 3,  2000·brochures,  3000-survey | Number of different kinds of promo material | 4000-flyers  2000· educational material  2-billboard,  2000·brochure  4000f·layers,  2000· educational materials 1,  2000 · educational materials 2,  5000· educational materials 3,  2000·brochures,  3000-survey | 100 | | **Result indicators** | | | | | | | Increased social and cultural integration of people in the border areas | Number of participants benefiting from cross-border social and cultural events | 10 Roma women educated, 30 Roma children educated, 50 Roma women educated | Number of participants benefiting from cross-border social and cultural events | 10 Roma women educated, 30 Roma children educated, 50 Roma women educated | 100 | |
| RESULTS ACHIEVED: | 10 Roma women educated;  500 Roma families visited;  30 children educated;  50 women educated;  500 hygiene packages distributed;  1 sport tournament implemented;  1 Music festival organized;  Project promotion implemented. |
|  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Partnership information** |  | | | | |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | Foundation Hemofarm | Serbia | South Banat | 145.900,00 | Vršac, Beogradski put bb  Tel. +381 13 830915 |
| PARTNER 2: | Gipsy Women Association „For our children” | Romania | Timiş | 114.000,00 | Timisoara, Dorobantilor Street no 42,  Tel: 0256/206083 |



1. the implementation period (including extensions) [↑](#footnote-ref-1)
2. total funds spent/total funds contracted \*100 [↑](#footnote-ref-2)
3. indicators and level of achievement against targets set [↑](#footnote-ref-3)