|  |  |
| --- | --- |
| **Project information** | |
|  |  |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1413 |
| PRIORITY AXIS: | 2.Environment and Emergency Preparedness |
| MEASURE: | 2.3 More effective systems and approaches to emergency preparedness |
| PROJECT TITLE: | **Joint Management of the emergency situations in Romania - Republic of Serbia cross-border area** |
| ACRONYM: | EmSit |
| DURATION[[1]](#footnote-1): | 17.04.2013 – 16.04.2015 |
| IPA FUNDS CONTRACTED: | 1.953.876,22€ |
| TOTAL FUNDS CONTRACTED: | 2.298.677,90€ |
| ABSORBTION RATE (%)[[2]](#footnote-2): | 79,47% |

|  |  |
| --- | --- |
| PROJECT OBJECTIVE(S): | Increasing the quality of life for the population of the Romania-Serbia border area by strengthening the institutional and technical management capacity in case of disaster and response in emergency situations.  Strengthening the cooperation of the competent authorities of the Romania-Serbia border region, reflected in the two-way exchange of information regarding emergency situations.  Increasing the monitoring and reaction capacity of the authorities in situations of natural disasters. |
| SHORT DESCRIPTION OF THE PROJECT: | Through implementation of this project the partners purchased specific equipment necessary for creating an efficient Management system in case of emergency situations in the cross-border area Mehedinti – Bor. |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DEGREE OF ACHIEVEMENT OF INDICATORS[[3]](#footnote-3): | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | **Indicator** | **Indicator value provisioned in the contract** | | **Present indicator value** | | **% 6= (5)/(3)\*100** | | | **Output indicators**  **(1)** | **UM**  **(2)** | **Quantity**  **(3)** | **UM**  **(4)** | **Quantity**  **(5)** |  | | | The institutional capacity and increased training for the reaction emergency situations in the field of environment | | | | | | | Technical preparation increased for emergency situations in the field of environment | | | | | | | Information Decision Making System for emergency situations | Unit | 1 | Unit | 1 | 100% | | | Joint actions in response to raise awareness of urgent situations | Unit | 2 work-shops  1 simulation exercise | Unit | 2 work-shops  1 simulation exercise | 100% | | | Number of purchased equipment | Unit | 2 operational mobile centres  126 equipment delivered | Unit | 2 operational mobile centres  126 equipment delivered | 100% | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **Result indicators**  **(1)** | **UM**  **(2)** | **Quantity**  **(3)** | **UM**  **(4)** | **Quantity**  **(5)** |  | | Institutional qualification in response to environmental emergencies | The number of new cross – border emergency plans drawn up or training events conducted on emergency planning and emergency management techniques | 2 workshops | The number of new cross – border emergency plans drawn up or training events conducted on emergency planning and emergency management techniques | 2 workshops | 100% | | A wider implementation of the national and EU legislation in the field of environment | The number of implementation activities, actions, initiatives and the national an EU legislative framework regarding the environment | 1 action | The number of implementation activities, actions, initiatives and the national an EU legislative framework regarding the | 1 action | 100% | |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| RESULTS ACHIEVED: | **1 integrated cross-border system for management of emergency situations**  The main result of the project is the implementation and operation of an integrated cross-border management system for emergency situations, which combined the state-of-the art technology in IT and field equipment.The project featured a high degree of innovation by introducing the use of latest IT technologies (hardware and software) for improving the management of emergency situations on both sides of the border.  1 implemented integrated information system  1 information system with 2 applications, as follows:   * **EMS application:** * Portal for authorized users; * Operational information module; * Optimal route calculation module; * Dangerous materials module; * Intervention resources management module; * Housing locations for evacuated persons management module; * Risk evaluation for emergency situations module; * Data integration module;   **Equipment for emergency situations**   * mobile communications centre, analysis, monitoring and coordination of interventions in emergency situations - 2 pcs; * perimeter surveillance and security system access - 2 pcs; * thermal infrared camera for firefighters (Thermal Imaging Camera Camera-Fire Fighting) - 2 pcs; * ATV fire - 6 pcs; * bags for fire extinguishers - Backpack Fire extinguisher -100 pc; * sliding scale fire - 12 items; * fire flashlights with batteries - 20 pieces;   boat -6 persons - 4 pcs  **2 common analysis workshops with 60 participants to both workshops**  **1 best practice guide for emergency situations** | | | | | |
| **Partnership information** | | |  | | | | | |
|  | | |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS | |
| LEAD PARTNER: | | | The Drobeta Inspectorate for Emergency Situations within the Mehedinti County | Romania | Mehedinți | 1.277.685,91 | Drobeta-Turnu Severin,  Str. Portului nr. 2  Tel. +40252311212 | |
| PARTNER 2: | | | Ministry of Interior of the Republic of Serbia | Serbia | Belgrade | 1.020.991,99 | Belgrade, Kneza Milosa 103  Tel. +381 11 3617 294 | |
| PARTNER 3: | | | The ”Semenic” Inspectorate for Emergency Situations within the Caras–Severin County | Romania | Caras–Severin | 0 | REŞIŢA,  Castanilor Street, no.123  Tel. +40255212639 | |



1. the implementation period (including extensions) [↑](#footnote-ref-1)
2. total funds spent/total funds contracted \*100 [↑](#footnote-ref-2)
3. indicators and level of achievement against targets set [↑](#footnote-ref-3)