| Project information |  |
| --- | --- |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1413 |
| PRIORITY AXIS: | 2.Environment and Emergency Preparedness |
| MEASURE: | 2.3 More effective systems and approaches to emergency preparedness |
| PROJECT TITLE: | Joint Management of the emergency situations in Romania - Republic of Serbia cross-border area |
| ACRONYM: | EmSit |
| DURATION: | 17.04.2013 – 16.04.2015 |
| IPA FUNDS CONTRACTED: | 1.953.876,22€ |
| TOTAL FUNDS CONTRACTED: | 2.298.677,90€ |
| ABSORBTION RATE (%): | 79,47% |

| PROJECT OBJECTIVE(S): | Increasing the quality of life for the population of the Romania-Serbia border area by strengthening the institutional and technical management capacity in case of disaster and response in emergency situations. Strengthening the cooperation of the competent authorities of the Romania-Serbia border region, reflected in the two-way exchange of information regarding emergency situations. Increasing the monitoring and reaction capacity of the authorities in situations of natural disasters. |
| --- | --- |
| SHORT DESCRIPTION OF THE PROJECT: | Through implementation of this project the partners purchased specific equipment necessary for creating an efficient Management system in case of emergency situations in the cross-border area Mehedinti – Bor. |

| DEGREE OF ACHIEVEMENT OF INDICATORS: | Indicator; Indicator value provisioned in the contract; Present indicator value; % 6= (5)/(3)*100. Output indicators (1); UM (2); Quantity (3); UM (4); Quantity (5). The institutional capacity and increased training for the reaction emergency situations in the field of environment. Technical preparation increased for emergency situations in the field of environment. Information Decision Making System for emergency situations; Unit; 1; Unit; 1; 100%. Joint actions in response to raise awareness of urgent situations; Unit; 2 work-shops 1 simulation exercise; Unit; 2 work-shops 1 simulation exercise; 100%. Number of purchased equipment; Unit; 2 operational mobile centres 126 equipment delivered; Unit; 2 operational mobile centres 126 equipment delivered; 100%. Result indicators (1); UM (2); Quantity (3); UM (4); Quantity (5). Institutional qualification in response to environmental emergencies; The number of new cross – border emergency plans drawn up or training events conducted on emergency planning and emergency management techniques; 2 workshops; The number of new cross – border emergency plans drawn up or training events conducted on emergency planning and emergency management techniques; 2 workshops; 100%. A wider implementation of the national and EU legislation in the field of environment; The number of implementation activities, actions, initiatives and the national an EU legislative framework regarding the environment; 1 action; The number of implementation activities, actions, initiatives and the national an EU legislative framework regarding the; 1 action; 100%. |
| --- | --- |

| RESULTS ACHIEVED: | 1 integrated cross-border system for management of emergency situations The main result of the project is the implementation and operation of an integrated cross-border management system for emergency situations, which combined the state-of-the art technology in IT and field equipment.The project featured a high degree of innovation by introducing the use of latest IT technologies (hardware and software) for improving the management of emergency situations on both sides of the border. 1 implemented integrated information system 1 information system with 2 applications, as follows: - EMS application: - Portal for authorized users; - Operational information module; - Optimal route calculation module; - Dangerous materials module; - Intervention resources management module; - Housing locations for evacuated persons management module; - Risk evaluation for emergency situations module; - Data integration module; Equipment for emergency situations - mobile communications centre, analysis, monitoring and coordination of interventions in emergency situations - 2 pcs; - perimeter surveillance and security system access - 2 pcs; - thermal infrared camera for firefighters (Thermal Imaging Camera Camera-Fire Fighting) - 2 pcs; - ATV fire - 6 pcs; - bags for fire extinguishers - Backpack Fire extinguisher -100 pc; - sliding scale fire - 12 items; - fire flashlights with batteries - 20 pieces; boat -6 persons - 4 pcs 2 common analysis workshops with 60 participants to both workshops 1 best practice guide for emergency situations |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Partnership information |  |  |  |  |  |  |  |  |
|  |  |  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |  |
| LEAD PARTNER: |  |  | The Drobeta Inspectorate for Emergency Situations within the Mehedinti County | Romania | Mehedinți | 1.277.685,91 | Drobeta-Turnu Severin, Str. Portului nr. 2 Tel. +40252311212 |  |
| PARTNER 2: |  |  | Ministry of Interior of the Republic of Serbia | Serbia | Belgrade | 1.020.991,99 | Belgrade, Kneza Milosa 103 Tel. +381 11 3617 294 |  |
| PARTNER 3: |  |  | The ”Semenic” Inspectorate for Emergency Situations within the Caras–Severin County | Romania | Caras–Severin | 0 | REŞIŢA, Castanilor Street, no.123 Tel. +40255212639 |  |

the implementation period (including extensions)

total funds spent/total funds contracted *100

indicators and level of achievement against targets set