
|  |  |
| --- | --- |
| **Project information** | |
|  |  |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1414 |
| PRIORITY AXIS: | 3. Promoting “people to people” exchanges |
| MEASURE: | 3.3 Increase educational, social cultural and sporting exchanges |
| PROJECT TITLE: | **Partnership for Promoting Green Energy in the Rural Area of the Romanian-Serbian Cross-border Region** |
| ACRONYM: | **GEROS** |
| DURATION[[1]](#footnote-1): | 06.10.2015 – 05.10.2016 |
| IPA FUNDS CONTRACTED: | 159.214,13€ |
| TOTAL FUNDS CONTRACTED: | 187.310,74€ |
| ABSORBTION RATE (%)[[2]](#footnote-2): | 91,05% |

|  |  |
| --- | --- |
| PROJECT OBJECTIVE(S): | Increase the level of awareness and information regarding the use of green energy in rural areas by know-how transfer in the cross-border area.  Creation of a group of opinion leaders having know-how in the green energy domain.  Improvement of the infrastructure for insuring better cooperation and knowledge transfer regarding green energy in the cross-border area.  Supporting better preparation for people to develop new activities and to find new jobs in the green energy domain in the cross border-area.  Promoting the importance of using green energy sources for a sustainable development among the population in the cross-border area. |

|  |  |
| --- | --- |
| SHORT DESCRIPTION OF THE PROJECT: | Through this project was created a Green Energy Promotion and Counselling Centre, a virtual network focused on the cooperation between the partners in the field of Green Energy <http://geros.ro/ro/acces-portal-geros-eu/>, one study on the potential of renewable energy sources. |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DEGREE OF ACHIEVEMENT OF INDICATORS[[3]](#footnote-3): | |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **Indicator** | **Indicator value provisioned in the contract** | | **Present indicator value** | | **% 6= (5)/(3)\*100** | | **Output indicators**  **(1)** | **UM**  **(2)** | **Quantity**  **(3)** | **UM**  **(4)** | **Quantity**  **(5)** |  | | Number of visits between partners for best practice exchange | pc. | 3 | pc. | 4 | 133.33% | | Number of Centre for Promoting and Counselling developed in the partnership | pc. | 1 | pc. | 1 | 100% | | Number of trainings for best practice dissemination | pc. | 2 | pc. | 2 | 100 | | Number of interactive information website regarding cross-border extracurricular activities within the project | pc. | 1 | pc. | 1 | 100 | | **Result indicators** |  |  |  |  |  | | Increased social and cultural integration of people in the border areas | Number of participants | 200 | Number of participants | 284 | 142% | | Increased cooperation between NGOs across the border in order to develop civil society capacity on border area | Number of activities, action plans, initiatives. | 2 | Number of activities, action plans, initiatives | 2 | 100% | | Improved quality of life and increased attractiveness of the border communities as a living place | Number of activities, actions, initiatives. | 10 | Number of activities, actions, initiatives | 10 | 100% | | Improved knowledge of culture, history, society, organizational and institutional structure, and language of the neighbouring country | Number of participants gained knew knowledge in events. | 40 | Number of participants gained knew knowledge in events. | 44 | 110% | |
| RESULTS ACHIEVED: | - 3 presentation of opportunities for cooperation between NGO from Ioan Slavici Foundation and EkoPokretTorak at Zitiste and ROSENC Timișoara  - 10 presentation at Promotion and counselling centre in Zitiste  - 1 virtual network created;  - green energy promotion and counselling Centre;  - 2 training, 1 cross border caravan, 284 people informed about renewable energy problem, completed procurement for organizing of caravan;  - 1 school competition, 16 projects presented by participants;  - 1 study on the potential of renewable energy sources;  - 2 closing seminars in RO and SRB, respective 56 and 36 participants;  - Editing, designing, printing and distribution of Brochures for Study, training, Cross-border caravan (in RO, EN and SRB language), School project competition and closing seminars (RO-EN, SRB- EN) |
|  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Partnership information** |  | | | | |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | “Politehnica” University of Timisoara | Romania | Timis | 108.782,00 | Timisoara, P-ta Victoriei nr. 2  Tel. 0040-744.264.650 |
| PARTNER 2: | Zitiste Municipality | Serbia | Central Banat | 49.583,74 | Zitiste, Cara Dusana 15  Tel. 00381-23-821-306 |
| PARTNER 3: | “Ioan Slavici” Foundation for Culture and Education | Romania | Timis | 28.945,00 | Timisoara, 21 Dr. Ioan Bontila street ap.2  Tel. +40256/213108 |



1. the implementation period (including extensions) [↑](#footnote-ref-1)
2. total funds spent/total funds contracted \*100 [↑](#footnote-ref-2)
3. indicators and level of achievement against targets set [↑](#footnote-ref-3)