|  |  |  |
| --- | --- | --- |
| **Project information** | | |
| CALL FOR PROPOSALS | 1 |
| MIS-ETC: | 428 |
| PRIORITY AXIS: | 3. Promoting “people to people” exchanges |
| MEASURE: | 3.3 Increase educational, cultural and sporting exchange |
| PROJECT TITLE: | **Cultural Heritage in Everyday Life in the Border Areas** |
| ACRONYM: | Cultural heritage |
| DURATION[[1]](#footnote-1): | 10.02.2011 – 09.02.2012 |
| IPA FUNDS CONTRACTED: | 80.840,95 € |
| TOTAL FUNDS CONTRACTED: | 95.107,00 € |
| ABSORBTION RATE (%)[[2]](#footnote-2): | 79,75% |
| PROJECT OBJECTIVE(S): | 1. Promotion of cultural heritage in the context of EU integrations; 2. Promotion and preservation of language and customs as cultural heritage in border region; 3. Promoting the cross-border cooperation. |

|  |  |
| --- | --- |
| SHORT DESCRIPTION OF THE PROJECT: | The partnership was created in order to research the traditions of the national minorities in the cross-border region, respectively the Serbian minority in the Romanian counties of Timiş and Caraș-Severin and the Romanian minority in the Serbian South Banat district. These national minorities have a very specific language, different than the languages of the majority of the Serbian and Romanian population. These specific language dialects are a cultural heritage and the project helped to preserve them by making an Anthology of interesting stories, a Bilingual lexicon and a short-films archive. Beside the language, a group of students studied and analysed the terminology concerning food and cooking, houses, clothing, customs in the family and local community, education, music, religion, fun in spare time, communication between people, traveling and newspapers. |
| DEGREE OF ACHIEVEMENT OF INDICATORS[[3]](#footnote-3): | |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **Indicator** | **Indicator value provisioned in the contract** | | **Present indicator value** | | **% 6= (5)(3)\*100** | | **Output indicators**  **(1)** | **UM**  **(2)** | **Quantity**  **(3)** | **UM**  **(4)** | **Quantity**  **(5)** | | Increased people-to-people exchange in the fields of education, culture and sports | Number of participants | 1000 | Number of participants | 1000 | 100% | | **Result indicators** |  |  |  |  |  | | Increased social and cultural integration of people in the border areas | Number of participants  benefiting from cross border  social and cultural  events | 150 students from both country | Number of participants  benefiting from cross border  social and cultural  events | 150 | 100% | | 100 inhabitants of villages in border regions | 100 | 100% | |  | 1000 people interested in project activities (students, teachers, parents, relatives, citizens, inhabitants, social institution and other entities) |  | 1000 | 100% | |

|  |  |
| --- | --- |
| RESULTS ACHIEVED: | 1. Formed students research groups (LP, P2, P3) 2. The website was designed and published (LP) 3. Finished research (LP, P2, P3) 4. Workshops were held (LP, P2, P3) 5. Bulletins was prepared and printed (LP) 6. Lexicon was printed and DVD was finished (LP) 7. Bilingual anthology of old stories was finished and printed (LP) 8. The musical and linguistic processing of old Serbian and Romanian folk songs was completed (LP) 9. Filming activities of short films and video-clips are finished (LP) 10. The festival was organized and performed (LP, P2, P3) |
|  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Partnership information** |  | | | | |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | Grammar School ”Borislav Petrov Braca” | Serbia | South Banat | 67.569 | Vršac, 1 Mihajla Pupina Street  Tel. +381 13 836448 |
| PARTNER 2: | College “Constantin Diaconovic Loga” | Romania | Timis | 19.184 | Timisoara, 37 B-dul C. D. Loga  Tel. 0256491873 |
| PARTNER 3: | Theoretical Grammar School “Dositej Obradovic” | Romania | Timis | 8.354 | Timisoara, B-dul Dragalina 6  Tel. 0256491624 |



1. the implementation period (including extensions) [↑](#footnote-ref-1)
2. total funds spent/total funds contracted \*100 [↑](#footnote-ref-2)
3. indicators and level of achievement against targets set [↑](#footnote-ref-3)