| Project information |  |
| --- | --- |
| CALL FOR PROPOSALS | 1 |
| MIS-ETC: | 440 |
| PRIORITY AXIS: | 3 Promoting “people to people” exchanges |
| MEASURE: | 3.3 Increase educational, cultural and sporting exchange |
| PROJECT TITLE: | CENTER FOR NUMERICAL SIMULATION & DIGITAL/RAPID PROTOTYPING |
| ACRONYM: | SIDIRA |
| DURATION: | 18.12.2010 – 17.12.2011 |
| IPA FUNDS CONTRACTED: | 169.563,10 |
| TOTAL FUNDS CONTRACTED: | 199.486,00 |
| ABSORBTION RATE (%): | 92,22 |
| PROJECT OBJECTIVE(S): | To create a center for Numerical Simulation & Digital/Rapid prototyping for educational purposes and to procure the technical equipment (hardware and software) of this technology. To conceive, elaborate and publish courses for Numerical Simulation and Digital / Rapid Prototyping technology. To promote courses in order to educate actual and future students from Romania & Serbia to learn /use the new Digital/Rapid Prototyping technology. To hold Workshop and conference. To conceive the WEB site for the project. To sustain visual & audio & newspaper mass media campaign for expanding the new technology knowledge’s in the region. |
| SHORT DESCRIPTION OF THE PROJECT: | Numerical Simulation has become a useful part of mathematical modelling of many natural systems in physics, chemistry and biology, human systems in economics, psychology, and social science and in the process of engineering new technology, to gain insight into the operation of those systems or to observe their behaviour. Digital Prototyping changes the traditional product development cycle from design > build > test > fix to design > analyse > test > build. Instead of needing to build multiple physical prototypes and then testing them to see if they’ll work, companies can conduct testing digitally throughout the process by using Digital Prototyping, reducing the number of physical prototypes needed to validate the design. Rapid Prototyping can be defined as a group of techniques used to quickly fabricate a scale model of a part or assembly using three-dimensional computer aided design data. The project offered the possibility to create a centre based on these new technologies for the academic world, to acquire the necessary equipment and to apply these technologies in the education process of an engineering student in Eftimie Murgu University from Resita, Romania and Technical College of Applied Sciences in Zrenjanin, Serbia. The project created the basis for both the current and the future educational cooperation in using this technology enabling the students to learn how industrial manufacturers use the results of this new technology to accelerate time to market, reduce cost, increase product safety, and improve product quality, primarily reliability and performance. |
| DEGREE OF ACHIEVEMENT OF INDICATORS: | Indicator value provisioned in the contract; Present indicator value; % 6= (5)/(3)*100. Output indicators (1); UM (2); Quantity (3); UM (4); Quantity (5). Increased people-to-people exchange in the fields of education, culture and sports. Result indicators. Increased people-to-people exchange in the fields of education, culture and sports; Number of people participated in cross-border people-to-people exchanges events; 48; Number of people participated in cross-border people-to-people exchanges events; 50; 104. Project indicators. Involved students in the fields of education; Number of students participated in educational events; 32; Number of students participated in educational events; 36; 112. Educational courses resulted from the project; Number of written educational courses resulted from the project; 2; Number of written educational courses resulted from the project; 2; 100. Involved people in the conference activities; Number of Involved people in the conference activities; 100; Number of Involved people in the conference activities; 152; 152. |
| RESULTS ACHIEVED: | • The Centre for Numerical Simulation & Digital/Rapid prototyping within Eftimie Murgu University was created and equipped with 3D Scanner, 3D Printer, SolidWorks professional software, CNC Machine Tool, laptop, projector and relevant accessories in order to teach students using a practical approach. •”Digital prototyping & numerical simulation with Solid Works software” course was published and used in the educational process in both Romania and Serbia. • “Casting applications with AnyCasting software” course was published and used in the education process in both Romania and Serbia. • CNC machining & SolidCAM Workshop with Romanian and Serbian students was accomplished. The Workshop with Romanian and Serbian students was held in Zrenjanin (29 November - 30 November 2011). A short video about the project is available at: https://www.youtube.com/watch?v=Ykj9vP9k85A |

| Partnership information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | “EFTIMIE MURGU” UNIVERSITY OF RESITA | Romania | CARAŞ-SEVERIN | 151.896,00 | RESITA, P-TA TRAIAN VUIA Tel. +40 255 210227 |
| PARTNER 2: | TECHNICAL COLLEGE OF APPLIED SCIENCES IN ZRENJANIN | Serbia | SREDNJE-BANATSKI | 47.590,00 | ZRENJANIN, DJORDJA STRATIMIROVIĆA 23 Tel. +38123565005 |

the implementation period (including extensions)

total funds spent/total funds contracted *100

indicators and level of achievement against targets set