|  |  |
| --- | --- |
| **Project information** | |
|  |  |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1317 |
| PRIORITY AXIS: | 1.Economic and Social Development |
| MEASURE: | 1.1 Support for local/regional economic and social infrastructure |
| PROJECT TITLE: | **Green Lights for Safety and Sustainability of Roads** |
| ACRONYM: | GLOSS |
| DURATION[[1]](#footnote-1): | 11.12.2013 – 10.12.2015 |
| IPA FUNDS CONTRACTED: | 586.945,81 |
| TOTAL FUNDS CONTRACTED: | 690.524,48 |
| ABSORBTION RATE (%)[[2]](#footnote-2): | 93,92 |
| PROJECT OBJECTIVE(S): | * Achieving a more balanced and sustainable socio-economic development of the Romanian-Serbian border area. * The development of tourism in Vrsac and Deta through the modernization of the infrastructure in order to access tourism attractions. * Achieving joint development and promotion of tools and techniques to encourage the sustainable use of resources. * Promoting the exchange of good practice. * Improvement of the quality of life for the communities of the border area. |
| SHORT DESCRIPTION OF THE PROJECT: | The project consisted of the introduction of new technology in illumination which increased the attractiveness of the road, and thus contributed to economic development through increased tourists’ visits to the region. 874 new street lights were installed in Vrsac and 50 in Deta.  The goal of the project was to encourage sustainable use of energy through effective technology of street lighting. Partners procured a car and equipment: FLIR thermal imaging camera and luxmeter DeltaOhm. An automatic control and data acquisition system for public lighting was installed in Vrsac. |
| DEGREE OF ACHIEVEMENT OF INDICATORS[[3]](#footnote-3): | |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **Indicator** | **Indicator value provisioned in the contract** | | **Present indicator value** | | **%**  **6= (5)/(3)\*100** | | **Output indicators**  **(1)** | **UM**  **(2)** | **Quantity**  **(3)** | **UM**  **(4)** | **Quantity**  **(5)** |  | | Modernization of streets lighting in Vrsac | Number of  new street lights | 287 | Number of  new street lights | **874** | 304,5 % | | Modernization of streets lighting in Deta | Number of  new street lights | 50 | Number of  new street lights | **50** | 100% | | Energy savings from Modernization of streets lighting in Vrsac and Deta | [kWh/a] | 270,000 | [kWh/a] | **286.740**  **(Vrsac)**  **56,000**  **(Deta)** | 127 % | | Cost savings from Modernization of streets lighting in Vrsac and Deta | [€/a] | 15,000.00 | [€/a] | **23,926.34**  **(Vrsac)**  **4,000.00**  **(Deta)** | 186% | | Reduction in greenhouse gas emissions | [t/a] | 270 | [t/a] | **301.08**  **(Vrsac)**  **56.00**  **(Deta)** | 132% | | Increasing of visitors due to Modernization of streets lighting in Vrsac and Deta | Number of visitors | 7000 | Number of visitors | **20,000**  **(Vrsac)**  **3,000**  **(Deta)** | 328% | | Increasing of income from tourism due to Modernization of streets lighting in Vrsac and Deta | [€/a] | 560,000.00 | [€/a] | **587,452.00**  **(Vrsac)**  **120,000.00**  **(Deta)** | 126% | | **Result indicators** | | | | | | | Improved physical infrastructure in the border area | Number of infrastructure investment projects (calculated also by type). | 2 | Number of infrastructure investment projects (calculated also by type). | 2 | 100% | |
| RESULTS ACHIEVED: | * 100,000 citizens of Vrsac and Deta informed about the project and the energy and cost savings and its environmental impact (organized press conferences and workshops in Vrsac and Deta, printing and distribution of brochures and promotional materials, TV and radio spot etc.) * Purchased the equipment (Car Dacia Duster, FLIR thermal imaging camera and luxmeter DeltaOhm, automatic control and data acquisition system for public lighting) in Vrsac. * Prepared technical documentation for infrastructure works in Vrsac and Deta. * Realized rehabilitation works for the public lighting in Vrsac and Deta. |
|  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Partnership information** |  | | | | |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | Public Enterprise “Varos” (now City of Vrsac) | Serbia | South Banat | 440.013,60 | Vrsac, Dvorska 10a  Tel. +381 13821614 |
| PARTNER 2: | Deta Municipality | Romania | Timis | 250.510,88 | Deta, Victoriei, No 32  Tel. +40 723 686 786 |



1. the implementation period (including extensions) [↑](#footnote-ref-1)
2. total funds spent/total funds contracted \*100 [↑](#footnote-ref-2)
3. indicators and level of achievement against targets set [↑](#footnote-ref-3)