|  |  |
| --- | --- |
| **Project information** | |
|  |  |
| CALL FOR PROPOSALS | 2 |
| MIS-ETC: | 1338 |
| PRIORITY AXIS: | 1.Economic and Social Development |
| MEASURE: | 1.3 Promote SME development |
| PROJECT TITLE: | **Training to the Romanian-Serbian cross-border labour market** |
| ACRONYM: | TRAININGLAB |
| DURATION[[1]](#footnote-1): | 22.01.2014 – 21.01.2015 |
| IPA FUNDS CONTRACTED: | 251.472,50 € |
| TOTAL FUNDS CONTRACTED: | 295.850,00 € |
| ABSORBTION RATE (%)[[2]](#footnote-2): | 90,65% |

|  |  |
| --- | --- |
| PROJECT OBJECTIVE(S): | * Supporting the SMEs to increase their competitiveness through trainings. * Surveying and assessing the training-needs of local and regional SMEs. * Elaborating accurate curricula of the training courses. * Training of workers and job seekers. * Providing the opportunity of e-Learning. * Organizing informational days and workshops making companies and job seekers to meet |
| SHORT DESCRIPTION OF THE PROJECT: | The “Training to the Romanian-Serbian cross-border labour market” project was implemented in order to give support for small and medium sized businesses in the border region and especially in the two applicant organizations’ settlements and region by establishing cross-border information facilities for the business environment, by capacity building and strategic partnership building through joint workshops, trainings and eLearning courses for better economic cooperation in the labour market of the Romanian-Serbian border area. The project offered several training possibilities for long term unemployment persons after surveying the SME sector labour needs, promoting professional re-training, job search facilities, counselling activities through local informational points, providing labour market consultation services for job seekers, supporting the local employment of disadvantaged groups as well.  An E-learning platform system was developed, the E-learning training had 84 participants. Also, the classroom trainings had 129 participants |
| DEGREE OF ACHIEVEMENT OF INDICATORS[[3]](#footnote-3): | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | **Indicator** | **Indicator value provisioned in the contract** | | | **Present indicator value** | | **% 6= (5)/(3)\*100** | | **Output indicators**  **(1)** | **UM**  **(2)** | **Quantity**  **(3)** | **UM**  **(4)** | | **Quantity**  **(5)** |  | | Number of trained people | person | 180 | person | | 222 | **123,33** | | SMEs and firms reached | piece | 100 | piece | | 112 | **112** | | Accredited training syllabus | piece | 1 | piece | | 3 | **300** | | Workshops and info days | participant | 1400 | participant | | 1400 | **100** | | Database | piece | 3 | piece | | 4 | **133,33** | | **Result indicators** | | | | | | | | Increased SME’s capacity in the border area | Number of activities, actions, initiatives focusing on promoting SME’s activity | 12 | Number of activities, actions, initiatives focusing on promoting SME’s activity | | 12 | **100** | | Revealing the problems of the SME sector | Number of databases elaborated | 3 | Number of databases elaborated | | 4 | **133,33** | | Amending the situation of the SMEs in the border region | Number of business firms reached by the action | 100 | Number of business firms reached by the action | | 112 | **112** | | Increasing knowledge of the people in the cross border area | Number of participants successfully trained | 180 | Number of participants successfully trained | | 222 | **123,33** | | Strengthening the cooperation between the public and the private sector | Number of entities involved in new contacts | 300 | Number of entities involved in new contacts | | 300 | **100** | | Helping the spread of modern knowledge | Number of equipment purchased | 2 | Number of equipment purchased | | 2 | **100** | | Promotion of the Romanian-Serbian cross-border cooperation. | Number of information materials | 3000 | Number of information materials | | 5000 | **166,66** | |
| RESULTS ACHIEVED: | Elaborated training syllabi created for three modules that will remain and stay available within the e-learning system.  Three accredited training syllabi.  2 servers purchased  7 information days and 5 workshops held. |
|  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Partnership information** |  | | | | |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | Centre for Information and Development of the Tisza region | Serbia | North Banat | 154.000,00 | Kanjiza, Doža Đerđa 4  Tel. +381 24 873 151 |
| PARTNER 2: | Timis Chamber of Commerce, Industry and Agriculture | Romania | Timis | 141.850,00 | Timisoara, Piata Victoriei nr.3  Tel. +40.374160832 |





1. the implementation period (including extensions) [↑](#footnote-ref-1)
2. total funds spent/total funds contracted \*100 [↑](#footnote-ref-2)
3. indicators and level of achievement against targets set [↑](#footnote-ref-3)