| Project information |  |
| --- | --- |
| CALL FOR PROPOSALS | 2 |
| e-MS Code: | RORS-279 |
| PRIORITY AXIS: | 2 Environmental protection and risk management |
| OBJECTIVE: | 2.1 Environmental protection and sustainable use of natural resources |
| PROJECT TITLE: | Cross-border network for education and research of natural resources |
| ACRONYM: | NeteRNR |
| DURATION: | 05.02.2020 – 04.01.2023 (31 months and 29 days) |
| Interreg-IPA FUNDS CONTRACTED: | €894.437,79 |
| TOTAL FUNDS CONTRACTED: | €1.052.279,77 |
| ABSORPTION RATE (%): | 96,87 % |
| PROJECT OBJECTIVE(S): | The overall objective of the project was to establish a cross-border monitoring and educational network that gathers data by analysing soil and water for pollution originating from intensive agriculture. Data collected is to be shared with users, authorities and resident population in order to promote protection and sustainable use of environmental resources. |
| SHORT DESCRIPTION OF THE PROJECT: | Pollution is a global problem that affects all of us, including our cross-border region! All living things — from one-celled microbes to humans and whales — depend on Earth’s supply of air and water. Unfortunately, many things that are useful to people produce pollution that cause adverse change of the natural habitat damaging the quality of air, water and land. „Cross-border network for education and research of natural resources” project was dealing with common challenges in protection and sustainable use of main natural resources in the cross-border region of South Banat District and Timis County. Find out more about the project here: https://bit.ly/3qGqkm7 and here: https://www.facebook.com/NeteRNR |
| DEGREE OF ACHIEVEMENT OF INDICATORS: | 2 Infrastructure, equipment built/ installed/ modernized in the field of cross border services for environmental protection. 100% 780 Participants to project initiatives and events for information and awareness raising. 147% 3 Studies in the field of environmental protection and emergency management. (technical and scientific studies, researches in the relevant fields) 433% 2 Monitoring systems established/ extended/ modernized in the eligible area in the field of environmental protection and emergency management. 100% |
| RESULTS ACHIEVED: | 2 Monitoring systems established. 100% 180 users of natural resources and responsible authorities informed and educated. 291% 600 participants to seminars raising awareness on natural resources and their sustainable use. 104% 2 Scientific studies on the condition of natural resources using established monitoring systems. 600% 1 Guideline book developed. 100% 2 Monitoring system established. 100% |

| Partnership information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | Banat’s University of Agricultural Sciences and Veterinary Medicine “King Michael I of Romania” from Timisoara | Romania | Timis | 473.336,02 | Calea Aradului, no 119, Timisoara, Romania Phone: +40745 567024 rectorat@usab-tm.ro |
| PARTNER 2: | Regional development agency Južni Banat Ltd Pančevo | Serbia | South Banat | 578.943,75 | Karadjordjeva no. 4, Pancevo, Serbia Phone: +381 648789137 E-mail: igor.knezevic@rrajuznibanat.rs |

the implementation period (including extensions)

total funds spent/total funds contracted *100

indicators and level of achievement against targets set