| Project information |  |
| --- | --- |
| CALL FOR PROPOSALS | 2 |
| e-MS Code: | RORS-314 |
| PRIORITY AXIS: | 1 Employment promotion and services for an inclusive growth |
| OBJECTIVE: | 1.3 Social and cultural inclusion |
| PROJECT TITLE: | Supporting preventive-developmental needs of the youth ‘’Creativity Without Frontiers’’ |
| ACRONYM: | CWF |
| DURATION: | 09.10.2019 – 08.11.2020 (12 Months) |
| Interreg-IPA FUNDS CONTRACTED: | €147.970,38 |
| TOTAL FUNDS CONTRACTED: | €174.082,80 |
| ABSORPTION RATE (%): | 87% |
| PROJECT OBJECTIVE(S): | To contribute to preventing school truancy of vulnerable groups - a strategic approach (elaborating strategy documents in the field of supporting and strengthening youth at the level of developmental and non-developmental (stresses) crisis, diverting them from streets and risky behaviour in Bor municipality and city of Resita based on National Youth Strategies of Romania and Serbia). To strengthen the network of trained teams to support the socio-cultural integration and increase the potential of youth within the cross-border communities involved to challenge and decrease marginalization in Bor and Caras-Severin County. To develop a functional mechanism of support to preventive–developmental needs of youth and cultural connection while integrating cross-border communities in Bor District and Caras – Severin County. To promote joint activities and practice transfer, increasing awareness of inclusion and preventing school leaving (truancy) in cross-border communities in Bor and Caras – Severin County. |
| SHORT DESCRIPTION OF THE PROJECT: | More youth are involved in substance abuse, destructive behaviour, low achievement, school leaving, and communities lack mechanisms of enabling quality, continuous and comprehensive monitoring, support and empowerment of this group. The target group consists of young people, 10-19 years old. The project developed a preventive development support model for youth through clubs with inclusive content, encouraging and stimulating prosocial behaviour, diverting from risky behaviour and supporting continuing schooling. It encouraged socio-cultural inclusion and provided a connection over the border. The key activities were: - Educating educators (44) preventive activities leaders (’’Creating and leading support group helping youth at risk and training team increasing social and emotional maturity” and joint training of volunteers (20), intercultural exchanges, joint cross-border cultural-artistic youth expression (40) and exchange of good practices (24), - Establishing clubs for supporting preventive–developmental needs of youth in Bor and Resita (technical equipping of two Clubs and a mobile club and organizing activities), - Implementation group of preventive - developmental club activities in Bor and Resita; exercises strengthening youth to continue schooling, workshops increasing social skills and inclusion of youth (artistic workshops), - Transfer of practice increasing awareness of social and cultural inclusion, Activities in the community: organizing two final regional conferences and final concert in Bor and Caras-Severin County -joint cross-border cultural-artistic exchange. |
| DEGREE OF ACHIEVEMENT OF INDICATORS: | 2465 citizens involved in project activities in cultural, social health care services. 160% 4 Investments in health care and social services infrastructure. 100% 162 joint actions targeting vulnerable groups (youth, women, disabled, ethnic minorities) established for the prevention of early school leaving, for cultural inclusion 100% 212 participants in projects promoting gender equality, equal opportunities and social inclusion across borders 100% |
| RESULTS ACHIEVED: | 2465 citizens involved in project activities in cultural, social healthcare services. 160% 1 effective model of inclusive sociocultural contents in three established functional clubs for preventive developmental needs of youth and cultural activities of connecting, integration and improvement of cross-border area of Bor and Caras-Severin County. 100% 2 networks of trained teams. 100% 212 participants in projects promoting gender equality, equal opportunities and social inclusion across borders. |

| Partnership information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | COUNTRY | COUNTY/DISTRICT | BUDGET(EURO) | CONTACT DETAILS |
| LEAD PARTNER: | Association of citizens ''KOKORO'' - Bor | SERBIA | Borski | 71.832,60 | Save Kovačevića no. 15, 19210 Bor, kokorom@mts.rs |
| PARTNER 2: | NATIONAL COLLEGE “MIRCEA ELIADE” RESITA | ROMANIA | Caras Severin | 38.079,20 | Fagarasului no. 6-8, 320059, Resita, cris_lerch@yahoo.com |
| PARTNER 3: | TEACHING CORPUS HOUSE CARAS-SEVERIN Resita | ROMANIA | Caras Severin | 49.006,00 | Bega no. 1, 320162, Resita, nicolrd@yahoo.com |
| PARTNER 4: | Association of citizens ’’VILLAGE’’ Movement for rural development of Zlot | SERBIA | Borski | 15.165,00 | Pere Radovanovica no. 1, 19215, Zlot vilagebor@gmail.com |

the implementation period (including extensions)

total funds spent/total funds contracted *100

indicators and level of achievement against targets set